## Project Plan
S. No. | Activity | % Completed | Dependency | Target Completion Date | Remarks
1 | Business Requirement Document (BRD) | 95% | SMART programme inputs |  | docs/SRSE_BRD.docx v1.1 — stakeholder narrative, workflow prose, config backup §10; aligned with TDD v1.2. Pending sign-off.
2 | Design Document | 98% | 1 |  | docs/SRSE_Technical_Design_Document.docx v1.2 — stakeholder overview, service catalog, JSON config, Analysis engine; PPT Part B.
3 | Platform scaffold | 100% | 2 |  | Docker Compose, DB2 (operational) + Presto (analytical), and DATA_MODE synthetic/live switch proving both planes connect.
4 | Rule Engine | 95% | 3 |  | DMN-shaped AST, SQL compiler with bound parameters only, unit-tested; maps officer fields to physical columns via metadata.
5 | Execution service | 90% | 4 |  | Push-down count/breakdown/cohort against Presto; query timeout, aggregate-only results, fixed breakdown dimensions, cohort hard cap.
6 | Metadata & mapping | 90% | 3 |  | Field catalogue and per-mode column mappings in DB2; admin editor; Caffeine-cached resolver for rule and preview paths.
7 | Lakehouse registry & Analysis metadata | 90% | 6 |  | Register Silver/Gold tables; live column introspection; compare-as and fuzzy flags for cross-type and name matching.
8 | Officer Rules UI | 85% | 4, 6 |  | Rule builder, threshold sliders/selects, simulation results, district/gender/age breakdown tables and charts (e.g. Ekal Naari).
9 | Scenario store & comparison | 75% | 4, 8 |  | Save ruleset + result snapshots; load and pairwise compare breakdown deltas when thresholds change.
10 | Cohort drill-down API | 80% | 5 |  | Row-level sample endpoint with server-enforced cap; reports truncation so samples are not mistaken for full cohorts.
11 | Cohort drill-down UI | 40% | 10 |  | Officer-facing drill-down from simulation results; API exists; UI wiring and UX still limited.
12 | Analysis: single-table match | 100% | 7 |  | Two-table join on registered columns; exact/fuzzy match; NDJSON stream and full CSV download from Presto.
13 | Analysis: display-only columns | 100% | 12 |  | Extra columns in result grid only—not used in join keys—so officers see context without changing match logic.
14 | Analysis: multi-target hub match | 100% | 13 |  | One hub vs N targets (separate joins); progress events; time budget; partial failure per target; CSV all-or-nothing.
15 | Analysis: column groups (COMBINE / ANY_OF) | 95% | 13 |  | Multi-column criteria, name folding, UNNEST-based ANY_OF; SQL checked against Presto 0.297 parser in tests.
16 | Analysis: manual E2E on Presto | 80% | 15 |  | Container-based cross-catalog runs when match SQL changes; not fully automated in CI.
17 | Admin (lakehouse, mapping, backup) | 95% | 6, 7 |  | Table registration, field mapping editor, scheme settings, JSON export/import for operational config backup.
18 | Configuration files | 88% | 3 |  | Runtime config: application.yml, Spring profiles, guardrail/analysis properties, JDBC URLs, DATA_MODE and auth mode; docker-compose.yml and client-dev overrides; env-var catalogue for deploy.
19 | Configuration guide (documentation) | 85% | 18 |  | Human-readable ops doc: what each setting does, local vs client-dev values, troubleshooting (CONFIGURATION_GUIDE).
20 | Code quality (SonarQube) | 100% | — |  | Java and TypeScript issues addressed for maintainability and CI quality gate.
21 | Frontend lint cleanup | 30% | — |  | Remaining ESLint errors in legacy components outside Analysis; build passes but lint debt remains.
22 | Test cases | 85% | 4–16 |  | docs/SRSE_Test_Cases.xlsx — 40 SIT/UAT cases with BRD/TDD traceability; automated backend suite (~300+ unit/integration tests) separate.
23 | SIT | 25% | 22, 25–27 |  | End-to-end integration on synthetic stack and client-dev Presto/DB2: rules, Analysis, admin, auth seams.
24 | Client Dev profile | 70% | 3, 18 |  | Compose profile and settings to point at on-prem lakehouse and DB2; verified in slices; full stack boot sign-off pending.
25 | Presto JDBC confirmation | 0% | Lovadeep / IBM |  | Confirm PrestoDB (not Trino) driver coordinates for watsonx.data 2.3.1 against live endpoint.
26 | Golden Layer naming & mappings | 30% | Lovadeep / DBA |  | Replace placeholders with real catalog.schema.table.column bindings for LIVE mode.
27 | SRSE DB2 placement | 50% | Lovadeep |  | Final decision on operational schema/instance for SRSE-owned JPA entities.
28 | Derived fields (REL-01, etc.) | 40% | Lovadeep / data eng. |  | Confirm Tier-3 fields pre-materialised upstream (e.g. income 3-yr avg) before officers map them.
29 | Live lakehouse seed & validation | 40% | 26, 28 |  | Register production tables, complete mappings, run representative scheme simulations on live data.
30 | Auth (RajSewadwar SSO) | 20% | Arvind |  | Mock JWT and STATE_OFFICER gate locally; production SSO payload parsing still stubbed, fails closed.
31 | Security review | 0% | 24, 30 |  | Client-environment review of auth, injection controls, and deployment surface.
32 | UAT | 0% | 23, 29, 30 |  | Departmental officers validate rules and Analysis workflows against agreed test cases.
33 | Deployment | 60% | 23, 24 |  | Two-container packaging, install steps, smoke checks, runbooks; production monitoring hooks TBD.
34 | Services inventory | 75% | 2 |  | Master list of REST capabilities and UI modules—developed vs planned—see Reference for row 34 tab.

## Reference for row 34
Service / capability | Status | Primary API / surface
Health & connectivity | Developed | HealthController, connection info/update
Decision / rules simulation | Developed | /api/decision/**
Presto execution | Developed | Count, breakdown, cohort (via decision layer)
Field catalogue & mapping | Developed | FieldCatalogController, FieldColumnMappingController
Scheme configuration | Developed | SchemeController
Scenario store & compare | Developed | Scenario APIs under decision
Lakehouse admin & browse | Developed | LakehouseAdminController, LakehouseCatalogController
Analysis column metadata | Developed | AnalysisColumnMetadataController
Record match / Analysis | Developed | RecordMatchController (single + multi, CSV)
Admin config backup | Developed | AdminConfigController
Officer UI | Developed (partial cohort UI) | Next.js frontend container
RajSewadwar SSO | To be developed | Production auth
Live Golden Layer catalogue | To be developed | Depends on DBA inputs
Formal SIT sign-off pack | To be developed | Row 23 on Project Plan
Production handover | To be developed | Row 33 on Project Plan

## Overall completion
Metric | Value
Overall % completed (simple average of all activities)
Activities counted
Note | Unweighted mean of % Completed on Project Plan tab. Update activity rows to refresh.